## PCC
No | Date | Category | Issue | Detail | Who | When |  | Complete
1 | Nov16 4.1 | PCC | PCC Training | Look at using material to look at Code of conduct and if useful use other sessions for following PCC’s | Mike and Gordon (plus all for Review) | COMPLETE |  | Y
2 | 2016-09-01 | PCC | Missions Co-ordinator required | PCC agreed to maintain current regular giving and organise a meeting to look at distribution of £500 surplus | Ann Cain and Sueli to review Mission giving- Sally to pass on info | COMPLETE | Completed- see new action 38 | Y
3 | Oct16 5.1 | PCC | Final Budget for weekend at home | Budget was £500, cost £562-PCC happy with this- closed | Gordon /Sally | COMPLETE |  | Y
4 | Ongoing | PCC | MAP process | PCC accepted new MAP for 2021- review Nov/Dec 2021 | Gordon | Nov/Dec 2021
5 | Ongoing | Positive Steps | PS project | Ongoing update to PCC at Business Meetings | Gordon (Mo) | March21 PCC
6 | Nov16 7a2 | Open Access | Reboot of OA P project | Progress suggestions, including involvement with older people and Re naming | OA Steering/management group | COMPLETE |  | Y
7 | Nov | Open Access | Homeless Shelter | Advise Steering group of 3-month limit for Brunswick Hosting | Mike | COMPLETE |  | Y
8 | Nov16 7a3 | Open Access | Ideas for rebranding | Food Club/Bank – investigate and implement | Progress refresh for 2017 | COMPLETE |  | Y
9 | Nov17 7a4 | Refurb and Fabric | Car Parking | Car park- chain/hook Provided |  | COMPLETE |  | Y
10 | 2018-11-01 | Young People | Work with 7-11’s | see Nov 13 minutes- Discussions with M13 - maybe discuss at June PCC. Raised as possible discussion area following RefUrb- see Action 88 |  | COMPLETE |  | Y
11 | 2016-09-01 | Young People | Flexible Senior Sunday school | Social media implications | Gordon | COMPLETE | Confirmed is WhatsApp group for Senior Sunday school Kids- PCC happy with this | Y
12 | Nov17 7b1 | Young People | Start-up of teenage Fellowship Group | Being progressed and started after half term - |  | COMPLETE |  | Y
13 | 2017-01-01 | Young People | No Lead Group | Leadership team to discuss or at 12/3 meeting | LT Team | COMPLETE | Sunday School/Youth leaders happy to be this group- Complete | Y
14 | Nov16 5.1b | Worship and Prayer | Implement concept of Simple church for period in 2017 | P&L discussed and ongoing work to see if can be used - Taize service suggested |  | COMPLETE | AGREED to have as part of wider discussion- COMPLETE | Y
15 | Nov16 5,1g | Worship and Prayer | Teaching | Use BELLS material for preaching and F Groups in Lent 2017- Lent Group to be set up - Completed |  | COMPLETE |  | Y
16 | Nov16 5.1h | Worship and Prayer | More Mission inputs into Sunday services | Use Intercessions and Notices to publicise and look to use in other slots | Mike and P&L team | COMPLETE |  | Y
17 | Nov16 5.1i | Worship and Prayer | Use Anchor as symbol and basis of 2017 Motto/ theme | Progress Implementation | Mike plus | COMPLETE |  | Y
18 | Nov16 5.1j | Worship and Prayer | More Prayer times/availably | 3rd Sunday evenings to be publicised following Lent Group -Also include 1st Sunday evenings | Judith/Simon/Mike/Gordon | COMPLETE | Complete- now praying 2 Sunday evenings a month | Y
19 | Nov16 5.1k | Worship and Prayer | Culture of invitation | Publicise Carol service etc.- |  | COMPLETE |  | Y
20 | 2016-01-01 | Worship and Prayer | Implications of Adult/Children split on teaching | discuss with Sunday school the details of this at meeting on 12/3- Completed |  | COMPLETE |  | Y
21 | Nov16 5.1d | Refurb and Fabric | To Develop Building changes | Vision document presented to PCC and PCC AGREED approval of same for use with communications with Stakeholders etc. |  | COMPLETE | Vision document, Design brief and stakeholder document all live and happening- Item Complete | Y
22 | 2016-09-01 | Refurb and Fabric | Heating Priority | PCC Agreed to proceed with two quotes from Allan Lever re Windows. installed 8-15/2. |  | COMPLETE |  | Y
23 | 2016-09-01 | Refurb and Fabric | Roof leaks | Quotes to be obtained for 3 specific areas- 1 obtained so far |  | COMPLETE | roof repairs complete but still at least 1 leak- further investigation ongoing - see new Item 35- COMPLETE | Y
24 | 2016-09-01 | Refurb and Fabric | Quinquennial | List created of actions- Monday Main starts 20/2 fortnightly |  | COMPLETE |  | Y
26 | Nov17 7a7 | Refurb and Fabric | Gas Heating not great | PCC Authorised replacement of broken radiator- various heating firms being chased |  | COMPLETE | Will not proceed with radiator replacement but upgrade heating in Lounge/Youth Room/Foyer. Proposal to be brought to May PCC- Monies agreed- COMPLETE | Y
27 | 2016-09-01 | Refurb and Fabric | Interval Project | "light box" idea will not happen - but possibilities if we have new notice board- Completed for now |  | COMPLETE |  | Y
28 | Nov16 5.1a | Worship and Prayer | Can our supportive/Friendly nature be made more missional? | To ask Helen G if she could run a session during 2017 - see new item (31) following discussions on Numbers - this item complete |  | COMPLETE |  | Y
29 | 2016-09-01 | Pastoral | Contact with Congregation | Cards- To ask someone to start process as all info now obtained - Handed over and complete |  | COMPLETE | Complete- handed over | Y
30 | 2017-01-01 | PCC | PCC Ground Rules | PCC agreed to adopt these rules from 2017/18 meetings and review same at pre AGM meting each year |  | COMPLETE |  | Y
31 | 2017-03-01 | Worship and Prayer | Small Numbers at Sunday services | 1. Website to be updated (ask Paul ) 2. November ATS to be used to discuss with wider congregation the issue | Mike/Simon | COMPLETE | Completed | Y
32 | 2017-03-01 | Refurb and Fabric | MBS Survey | Engage Waldron Architects |  | COMPLETE | Completed and returned | Y
33 | 2017-03-01 | Refurb and Fabric | Strategic meeting | Organise to discuss Budget, fundraising, plan, Architects etc. |  | COMPLETE | . Strategic decisions agreed at PCC- COMPLETE | Y
34 | 2017-03-01 | Refurb and Fabric | Solar Panels | Sign necessary legal docs | Simon/Gordon | COMPLETE | Completed and returned | Y
35 | 2017-05-01 | Refurb and Fabric | Leak in Worship room | Investigation and final repair | Gordon | COMPLETE | Completed - No leaks since end of May | Y
36 | Ongoing | Fabric | Reporting to PCC | Report required for each PCC as to progress -Roof and Burner issues to sort | Tim | Next PCC
37 | 2017-05-01 | Safeguarding | Safeguarding Officer | Naomi Harrision can take postion as Safeguarding officer - Traing to be progressed after easter | Jess | April PCC
38 | 2017-07-01 | Finance | Mission outside Parish -Regular updates | No change for 2021- sally to update Ann on any funds available | Sally | After Accounts for 2020 finalised
39 | 2017-07-01 | Positive Steps | Womens Group | Starts 9th October - Completed |  | COMPLETE |  | Y
40 | 2017-07-01 | Positive Steps | Cleaner/ Caretaker | Thanks to Gina and replacement PCC AGREED to proposals in report | Gordon/ Positive Steps | COMPLETE | Complete | Y
41 | 2017-07-01 | Young People | Messy Church | see item 10 and Nov 18 minutes- now combined with 10 | Completed | COMPLETE |  | Y
42 | 2017-09-01 | Young People | YPFG Whats App group | Implement | Completed | COMPLETE |  | Y
43 | 01/09/2017 & ongoing | Refurb and Fabric | Selection of Architects | Write to Selected Architect and begin Feasibility process | Gordon | COMPLETE | Completed | Y
44 | 2017-09-01 | Fabric | Kitchen Procedures | Suggest and Implement - ongoing with training - - happened 30th Jan Jess chasing actions/ implementation up - review in July - put back till September - Jess and Kay to implement . Final processes in place- Kay will ensure done |  | COMPLETE |  | Y | Y
45 | 2017-09-01 | Refurb and Fabric | Funding Team | Begin to bring together those who can assist in finances for ReFurb | Completed | COMPLETE |  | Y
46 | 2017-09-01 | Refurb and Fabric | Clear up within Church | Organise another clear up morning | Gordon | COMPLETE | Completed | Y
47 | 2017-09-01 | Finance | Funds available | Bible to be bought for Young People - Completed |  | COMPLETE |  | y
48 | 2017-12-01 | PCC | GDPR | Alteration to GDPR letter (Gordon)/ Remove those in regular congregation from Prayer list -Done |  | COMPLETE |  | Y | Y
49 | 2017-12-01 | Positive Steps | Volunteer Agreement | Completed by Jan PCC | Sally | COMPLETE |  | Y
49 | Ongoing | Fabric | Implement H&S policy actions | Review H&S Policy and do outside inspection . | Gordon/Tim | April PCC
51 | Ongoing | Refurb | ReFurb updates | Report on updated Numbers and meeting 9th March | Gordon | Update at next PCC
52 | 2018-01-01 | P&L | Teaching Priorities | Aug & Sept readings set- Changes after that- see minutes |  | COMPLETE | Complete | Y
53 | 2018-03-01 | Finance | Budget | High level budget to be examined - Not now required | Sally | COMPLETE | Completed | y
54 | 2018-05-01 | Fabric | Barnabas | Rents to increase by £10- Implement | Gordon | COMPLETE | Completed | Y
55 | 2018-05-01 | PCC | Meetings | Agree format for 2018/19 | ALL | COMPLETE | Agreed- at June PCC | Y
56 | 2018-06-01 | Positive Steps | Night shelter 2018/19 | Now part of PS report for PCC | Completed | COMPLETE | See written report | Y
57 | 2018-06-01 | P&L | Volunteer Sunday | SG talked about Sunday School leaders and helpers in service on 9/9 and asked for extra helpers. Will keep raising and will include other roles in future 2nd Sunday Services | Simon | COMPLETE | Completed | Y
58 | 2018-06-01 | P&L | Prayer Box/ Station for all week | Box will be sited at H&S evening in Dec. Process required on collection and dissemination of Prayer requests | Sally , Judith and Jess | COMPLETE | Completed | Y
59 | 2018-06-01 | P&L | Welcome Event | See New item 62 regarding Autumn Celebration in early Oct |  | COMPLETE | Complete | Y
60 | 2018-06-01 | P&L | Culture of invitation | Completed via P&L meet |  | COMPLETE |  | Y
61 | 2018-06-01 | P&L | Daily Prayer names | 1. Check Names 2. Use on Wednesdays and Sundays 3. Re-issue 1st Sunday of month -DONE- completed on 19/5 |  | COMPLETE |  | Y
62 | 2018-08-01 | 3 M's | Volunteer Celebration | Detail updated at Sept PCC meeting for 28th | Simon | COMPLETE | Completed | Y
63 | 2018-08-01 | Young People | Light Party | MB reported that HG had talked to M13 staff about this and Gabriel is to discuss with SG how they can partner with us at this. Small planning group to meet. | Simon | COMPLETE | M13 did all planning after initail chat with Jess and Gordon | Y
64 | 2018-11-01 | P&L | Communion Assts | Register/ advise Diocese | Simon | COMPLETE | Completed | Y
65 | 2018-11-01 | PCC | Safe Church Policy | Post signed copy | Gordon | COMPLETE | Completed | Y
66 | 2018-11-01 | P&L | Poster for Christmas | Idea to Paul K/ create a display | Jess | COMPLETE | Completed | Y
67 | 2018-11-01 | Young People | Safeguarding Sunday school | no Gaps again in JSS helpers- Complete | Jess |  |  | Y | Y
68 | 2018-11-01 | ReFurb | AVFS | Join | Sally | COMPLETE | Completed | y
69 | 2018-11-01 | ReFurb | Donations | . Idea that invoices still have some sort of reminder on about Refurb -Sally processing and will implement during summer |  |  | DONE | Y
70 | 2018-11-01 | 3 M's | Burns Night | Planning/ publicity | Simon/Jess | COMPLETE | Occurred- reviewed as part of MAP at March PCC | Y
71 | 2018-11-01 | 3 M's | Church weekend | Agreed 8-10 July 2022- discuss later in 2021 | Gordon/Simon | Sept 21 PCC
72 | 2018-11-01 | Young People | Brunswick as a case study | Feedback from YL meeting and send PCC copy of report . YL agreed to hold lightly recommendations and action now complete |  | COMPLETE |  | Y
73 | 2019-01-01 | PCC | Caretakers Contract | Re-issue and distribute | Gordon | COMPLETE | Completed | Y
74 | Ongoing | P&L | Christmas 2020 | See Dec PCC minutes for actions/outcomes | Jess |  | COMPLETE | Y
75 | 2019-01-01 | 3 M's | Events | Passover meal- food etc -Reviewed and comments made at May PCC- 2 events planned for Autumn (see action 85) | Completed | COMPLETE |  | Y
77 | 2019-01-01 | Positive Steps | Night shelter 2019/20 | Very Unlikley Night shelter will occur in 20/21- Item Complete |  | COMPLETE |  | Y
77 | 2019-01-01 | P&L | Mission Partners | Arrange Op Rest(28/4) and Tear Fund ( 30/6) | Simon and Ann | COMPLETE | Op Rest now 14/4 and Tear Fund booked | Y
78 | 2019-01-01 | PCC | AGM | Electoral roll and paperwork | Gordon and Ann | COMPLETE | All on track for 31/3/19 | Y
79 | 2019-03-01 | Fabric | Decorate Lounge | Mostly complete- actions to be run over to Maintenance weekend in June - Complete |  | COMPLETE |  | Y
80 | 2019-03-01 | Young People | Needs and changes in YPFG | YPFG will continue twice a month | Youth Leaders to review | Next YL meeting
81 | 2019-03-01 | Finance | Designated Reserves | Alter as agreed at March PCC for 2018 accounts - PCC agreed |  | COMPLETE |  | Y
82 | 2019-03-01 | PCC | Meetings for 2019/20 | Organise dates- Done, July date to remain same |  | COMPLETE |  | Y
83 | 2019-03-01 | Refurb | Phase 1 spend | How much of reserves to be spent -PCC agreed all of reserve if required | Completed |  |  | y | y
84 | 2019-05-01 | Fabric | Spruce up weekend | Wednesday evenings to complete work- possibly 27th July as well |  |  | COMPLETE | Y
86 | 2019-05-01 | 3 M's | Autumn events | Involve thanksgiving as part of Nov, ATS and think about an advent event - decided will not happen , but see action in MAP (104) for next year |  | COMPLETE |  | Y | Y
85 | 2019-05-01 | Safeguarding | Safeguarding references and Training | Jess to contact those 1or 2 left | Jess | Update at next PCC
86 | 2019-05-01 | Refurb | Tender Phase 1 | Check impact of negotiated tender on Funders -agreed will take each funder as it comes and will obtain quotes as necessary- Architects aware |  | COMPLETE |  | Y
87 | 2019-05-01 | PCC | Climate Change | Start work on 3 month/ 12 month actions- Review in March | Gordon/Jess/Edwin | Mar 21 PCC
88 | 2019-06-01 | PCC | Mission | To discuss implications of ReFurb on Mission priorities of church -part of 3rd Sunday discussions from Nov 19- review start of PCC year ? PCC discussed Feb 20 and happy with direction |  | COMPLETE |  | Y
89 | 2019-06-01 | PCC | Volunteering | Speak to 1 person about either PA to Teas and Coffees- didn't happen - still gaps on both |  | COMPLETE |  | Y | Y
90 | 2019-06-01 | P&L | Service Pattern | Review 4 weekly mix of service "types" at next P&L meeting -Agreed good format and should continue |  | COMPLETE |  | Y | Y
91 | 2019-06-01 | Pastoral | Ongoing issues | Continuing phoning - will review once regularly back in Church | Judith/Sally/Yuko/Jess Ann | Apl 21 PCC
92 | 2019-06-01 | PCC | Mission | How can we become for intentional in sharing our faith ? - 3rd Sunday discussion from Nov 19- review start of PCC year ? Agreed to laeve till 2021 | ALL | May 21 PCC
93 | 2019-06-01 | PCC | Process | Send out invites to PCC in Autumn 11/9, 17/10 and 12/11 |  | COMPLETE |  | Y
94 | 2019-06-01 | PCC | Policy | Equality Policy - alter as per PCC Discussion - Agreed at Sept 19 PCC |  | COMPLETE |  | Y | Y
95 | 2019-07-01 | PCC | Equality / inclusive church/ | PCC to agreed 3rd Sunday discussion from Nov 19- review start of PCC year ? Ongoing 3rd Sunday from start of 2020 - restart again in late 2021 (as per Diocese request) | ALL | 2021-07-01
96 | 2019-07-01 | PCC | Giving Thanks for Offerings | need to say thanks for offerings (bring plate down) - raise issue with Simon. |  | COMPLETE |  | Y
97 | 2019-09-01 | P&L | Children's Teaching | Review use of material - 30 day explore of new options - too expensive - may buy odd resources to assist- but complete |  | COMPLETE |  | Y | Y
98 | 2019-09-01 | Fabric | Barnabas | Chase Richard Y for MOU - ongoing | SIMON | Next PCC
99 | 2019-10-01 | Pastoral | Pastoral | PRINT Welcome Leaflet | Jess | Feb 21 PCC
100 | 2011-11-01 | Finance | Mission giving | Give outstanding Mission surplus to over 50's group for a missional event . Sally to confirm amount , Simon to discuss ideas with Mo - Done |  |  |  | Y
101 | 2019-11-01 | P&L | Mission slots | implement process to raise profile of Mission in services, Prayers and Notices. Agreed Complete |  |  |  | Y
102 | 2019-11-01 | Refurb | Giving | Bite size giving containers/ December ATS | Simon/ Gordon | 30th November | Complete ! | Y
103 | 2019-11-01 | PCC | MAP process | Update specific actions for priority 1 from preachers and leaders- Done at P&L |  |  | COMPLETED | Y
104 | 2019-11-01 | Finance | Minibus | Take minibus off raod - aim for new one in late Summer | SIMON | June PCC
105 | 2019-11-01 | 3 M's | Dates for 2020 | Quiz happened- Carol singing possible - difficult to plan for 2021 but MAP review may assist |  |  | COMPLETE | Y
106 | 2020-12-01 | P&L | Mission | To Follow lectionary until Easter, but raise Stepping Stones for Growth Profile | P&L | Completed- New P&L objective in MAP |  | Y
107 | 2020-01-01 | P&L | Misson | Create an "inside out" group to plan events and activities for 2021 (MAPP).2 possible course (SSFG or LILF) for 2021- see new MAP objective |  | Completed- New P&L objective in MAP |  | Y
108 | 2020-01-01 | PCC | Communication | Focus group met- PCC happy with format |  | Completed |  | Y
109 | 2020-01-01 | Young People | Misson | Experience Christmas happening - keep and update for 2021- See new MAP objective for 2021 |  | Completed- New objective in MAP |  | Y
110 | 2020-02-01 | PCC | Mission Support | Meeting between Simon and Ann ( &Others ) to create written description of role | Simon/Ann | Mar 21 PCC
111 | 2020-02-01 | PCC | Service start | Publicise 10.45 start and talk to others about it |  | COMPLETE |  | Y
112 | 2020-02-01 | PCC | Inclusivity Statement | post in church and website | Sally/ Judith | Feb 21 PCC
113 | 2020-07-01 | Finance | Gift to M13 | Discuss with M13 if need |  | COMPLETE |  | Y
114 | 2020-07-01 | Finance | Missions Extra Pot | Details of missiosn pot to Ann/ Sueli |  | COMPLETE |  | Y
115 | 2020-07-01 | PCC | Eco Church and Faitrade Church | Details of both to be supplied to Edwin and Andy to look at - see action 87 for ECO church . Nothing specific for Fairtrade |  | COMPLETE |  | Y
116 | 2020-07-01 | Safeguarding | Safeguarding Documents | See separate list of Actions on page 2- Jess will chase in early 2021- Actions completed removed | Jess & Others | march 21 PCC
117 | 2020-07-01 | PCC | Re-opening of buildings | Work towards services taking place |  | COMPLETE |  | Y
118 | 2020-11-01 | PCC | Mission Gifts | Publicise and action Decisions |  |  | COMPLETE | Y
119 | 2020-11-01 | PCC | Next meeting | Invite and arrange 10/12 |  |  | COMPLETE | Y
120 | 2020-12-01 | PCC | Heartedge | Formally join | Simon/Gordon | Jan 21 PCC | Completed | Y
121 | 2020-12-01 | PCC | Fairtrade | Sign Climate coalition declartion as church | Andy | Jan 21 PCC | Completed | Y
122 | 2020-12-01 | Refurb | Rear of Church Plans | Monthly update | Via Gordon | March 21 PCC
123 | 2020-12-01 | Positive Steps | Potential Project with Age Uk | course/ project with CAP - Grant with Age UK - Funding update | Simon/ Judith | March 21 PCC
124 | 2021-01-01 | P&L | Mission | Look at Stepping Stones for Growth and wider use in Church | P&L /PCC | Throughout 2021- Review Q4
125 | 2021-01-01 | P&L | Mission | Create an Inside out Group group to look at engagement with community during Lockdown | Jess | June21 PCC
126 | 2021-01-01 | P&L | Services | consider how we do services post lockdown this year and beyond | Simon/Jess/P&L | After next P&L meeting
127 | 2021-01-01 | Young People | Mission | "Experience" -Confirm plan for Easter when possible and plan for rest of year after this | Jess and Team | March 21 for Easter and June 21 ongoing
128 | 2021-01-01 | Young People | Mission | 2b Young People Fellowship Group- review and plan for 2021 | Jess(for PCC) and others | 2021-06-01
129 | 2021-01-01 | 3 M's | Planning | Community Celebrations- plan for outdoor events in 2nd half of 2021 including Christmas (105) | Positive Steps Manager and Rector | Update at Apl 21 PCC
130 | 2021-01-01 | 3 M's | Planning | Create a drama production for community - Christmas | Positive Steps Manager and Rector | Q3 2021
131 | 2021-01-01 | Positive Steps | Strategic meeting | Review Positive steps activities and relaunch following Pandemic | Positive Steps Manager , Rector and PS steering Group | Q2 2021
132 | 2021-01-01 | Climate Emergency | Actions | 1st 3 months actions | Climate Group | Apl 21 PCC
133 | 2021-01-01 | Climate Emergency | Actions | 12 months aims | Climate Group | Jan 22 PCC
134 | 2021-02-01 | Young People | Opening up spring 2021 | Advise SS leaders of PCC suggestions | Gordon | 2021-02-28
135 | 2021-02-01 | Safeguarding | PCC DBS | Simon to send links to PCC members who do not have a church DBS | Simon | March 21 PCC

## Safeguarding
Safeguarding
PCC Actions September 2020- with Timescales and who !
The current Church of England Safeguarding policy requires the PCC to undertake the following outstanding actions.
1. Appoint a safeguarding officer in addition to Simon- Jess/ Simon by APCM | COMPLETE
2. Adopt a policy statement on recruiting ex offenders- Jess to obtain and submit for November PCC |  | COMPLETE
3. Display how to contact safeguarding officers (including diocese safeguarding officers)- Gordon to put details around building when open again
4. Have a safeguarding risk assessment for every activity in church involving children or vulnerable adults and review regularly- Data base to create for activities and find RA template – Gordon and jess – Nov PCC
5. Add the “model safeguarding provision that can be attached to any hire of church premises agreement” to all of our booking requests that involve children or vulnerable adults (except for children’s birthday parties) https://www.churchofengland.org/safeguarding/promoting-safer-church/policy-practice-guidance/templates-resources Simon/Jess to give to Mo and also send out to all current users – add to database
6. PCC members must complete C0 online safeguarding training- NEW PCC members to complete training
7. Sunday school assistants and those assisting with children or young people must complete C0 online training & C1 face to face training. Jess contacting diocese to see if we can arrange 1 off Church training – Contact by APCM
8. Churchwardens and those leading Sunday school or other youth or Children’s work must complete C0 online safeguarding training and C1 and C2 face to face training- Jess contacting diocese to see if we can arrange 1 off Church training – Contact by APCM
9. Have written consent from parents for any children we are communicating with directly.- Checked with Naomi Harrision regarding over 11’s- no contact with under 11’s- COMPLETE
10. Read and adopt the safeguarding policy annually.-Gordon to distribute with Sept PCC minutes and ALL to read by Nov PCC when can be adopted . COMPLETE